## Sheet1
Assmptions |  |  | PM | 1
| We have AePS Provider API Access |  | FE | 2
| Authentication Module - Done |  | BE | 2
| Agent Onboarding Module - Done |  | QA | 1
Wallet Module - Done
User Module - Done
Scope Of Work
Web App Development BC+Admin Panel
|  | 1. Agent Onboarding Screens | Agent Onboarding Module | 8 | Documentation Verification will bring unforseen complexities like vKyc, External Agent Verification Status It also includes Admin Panel | FE+BE
|  | 2. Login Screen | Authentication Module | 2 |  | FE+BE
Personas |  | 3. Dashboard | Wallet Module | 2 | Depends on the complexity of UI design | FE+BE
|  | 4. Agent User Management | User Module |  | 1. Is there any requirement of Kyc of BC Agent Users (Employees) ?
| Agent | 5. Wallet and Transactions History | Wallet Module | 2 |  | FE+BE
| Bank | 6. AePS Screen
| Customer |  | 5.1 AePS Provider API Availability (Sandbox) | - | Assumptions, we already have
| AePS Provider |  | 5.2 Device Integration Code Development | 1 | Purchasing and installing the Biometric Devices 1. Fingerprint Sensor and other Biometric Sensor Devices 2. Required Software/Driver installed on the OS 3. Test Env (Windows/Linux), Possibly windows | FE/BE
| BBPS |  | 5.3 AePS Screen Development and Related Backend API Development to fill all the fields from User Side e.g. Fetch Supported Bank List | 2 |  | FE+BE
|  |  | 5.4 Backend code to send AePS transactions with Minimum Checks | 1 |  | BE
|  |  | 5.5 Secure Code and Exception Handling (FE + BE) | 1 |  | BE
|  |  | 5.6 Integrating and testing all transaction modes | 1 |  | BE + FE
|  |  | 5.7 QA and Testing | 1 |  | QA

## AePS WBS
T=Time required to Repostory Setup, Codebase Setup, Sandbox Env Setup, Procurement of required Resources
Module | Task | Time (T+N) (Week) | Dependencies | Blockers / Observations / Requirements | Resource
1. Agent Onboarding | UI Development for Agent Registration | 4 | Form design, validations, error handling | Complex KYC and document verification may require external APIs | FE
| Backend Development for Agent Registration | 3 | API creation, data validation | Handling different agent types and status workflows | BE
| External Verification Integration (vKYC, Status Check) | 4 | vKYC, external API integration | Dependency on third-party verification services; delays possible | BE
| Admin Panel for Agent Management | 4 | Agent approval workflow, filters, status management | Role-based access needed; requires real-time updates | FE + BE
2. Authentication | Login Screen Development | 2 | UI design, session handling | Support for multi-factor authentication (OTP, Biometric) required | FE
| Backend API for Authentication | 2 | Token generation, secure storage | Secure storage & encryption mechanisms must be implemented | BE
3. Wallet | Wallet Dashboard UI Development | 2 | Display balance, transaction summary | UI complexity depends on additional features like filters and reports | FE
| Backend APIs for Wallet Transactions | 3 | Credit/debit, reconciliation | Transaction processing time should be optimized for real-time updates | BE
4. User Management | UI for Agent User Management | 3 | Role-based access, user modifications | Need confirmation on whether BC Agent Users require KYC | FE
| Backend APIs for User Management | 3 | Access control, authentication | Proper access control policies must be defined | BE
| KYC Handling for Agent Employees (If Required) | TBD | Define process, integrate KYC service | May depend on regulatory guidelines; verification method unclear | BE
5. AePS Module | AePS Provider API Availability (Sandbox) | Assumed | Assumed ready | Any delay in API availability will impact all dependent modules | -
| Device Integration Code Development | 1 | Biometric device setup, OS driver installation | Device procurement, compatibility with OS (Windows/Linux) is crucial | FE + BE
| AePS UI & Backend API Development | 3 | Fetch bank list, transaction input fields, authentication | Requires Aadhaar authentication and biometric device SDK integration | FE + BE
| AePS Transaction Processing Backend Code | 2 | Transaction validation, submission | API rate limits and latency considerations | BE
| Secure Code & Exception Handling | 1 | Data security, error handling | Must comply with PCI DSS and Aadhaar security guidelines | FE + BE
| Integrating & Testing All Transaction Modes | 2 | Testing cash withdrawal, balance inquiry, mini statements | Requires sandbox environment with test banks | FE + BE
| QA and Testing | 1 | Functional & security testing | Edge cases (network failure, invalid biometric input) need thorough testing | QA
6. Final Testing & Deployment | System Integration Testing (SIT) | 2 | Test overall system flow | Dependency on completion of all modules | QA
| User Acceptance Testing (UAT) | 2 | User feedback, final approval | Requires active participation from stakeholders | QA + FE + BE
| Deployment and Go-Live Preparation | 2 | Production environment setup | Must have rollback plans in case of failures | DevOps

## AePS WBS (Full)
T=Time required to Repostory Setup, Codebase Setup, Sandbox Env Setup, Procurement of required Resources
Module | Task | Time (T+N) (Week) | Dependencies | Blockers / Observations / Requirements | Resource
1. Agent Onboarding | UI Development for Agent Registration | 4 | Form design, validations, error handling | Complex KYC and document verification may require external APIs | FE
| Backend Development for Agent Registration | 3 | API creation, data validation | Handling different agent types and status workflows | BE
| External Verification Integration (vKYC, Status Check) | 4 | vKYC, external API integration | Dependency on third-party verification services; delays possible | BE
| Admin Panel for Agent Management | 4 | Agent approval workflow, filters, status management | Role-based access needed; requires real-time updates | FE + BE
2. Authentication | Login Screen Development | 2 | UI design, session handling | Support for multi-factor authentication (OTP, Biometric) required | FE
| Backend API for Authentication | 2 | Token generation, secure storage | Secure storage & encryption mechanisms must be implemented | BE
3. Wallet | Wallet Dashboard UI Development | 2 | Display balance, transaction summary | UI complexity depends on additional features like filters and reports | FE
| Backend APIs for Wallet Transactions | 3 | Credit/debit, reconciliation | Transaction processing time should be optimized for real-time updates | BE
4. User Management | UI for Agent User Management | 3 | Role-based access, user modifications | Need confirmation on whether BC Agent Users require KYC | FE
| Backend APIs for User Management | 3 | Access control, authentication | Proper access control policies must be defined | BE
| KYC Handling for Agent Employees (If Required) | TBD | Define process, integrate KYC service | May depend on regulatory guidelines; verification method unclear | BE
5. AePS Module | AePS Provider API Availability (Sandbox) | Assumed | Assumed ready | Any delay in API availability will impact all dependent modules | -
| Device Integration Code Development | 1 | Biometric device setup, OS driver installation | Device procurement, compatibility with OS (Windows/Linux) is crucial | FE + BE
| AePS UI & Backend API Development | 3 | Fetch bank list, transaction input fields, authentication | Requires Aadhaar authentication and biometric device SDK integration | FE + BE
| AePS Transaction Processing Backend Code | 2 | Transaction validation, submission | API rate limits and latency considerations | BE
| Secure Code & Exception Handling | 1 | Data security, error handling | Must comply with PCI DSS and Aadhaar security guidelines | FE + BE
| Integrating & Testing All Transaction Modes | 2 | Testing cash withdrawal, balance inquiry, mini statements | Requires sandbox environment with test banks | FE + BE
| QA and Testing | 1 | Functional & security testing | Edge cases (network failure, invalid biometric input) need thorough testing | QA
6. Debit CARD/RUPAY Transactions | RUPAY API Integration | 2 | API availability from switch provider | Must comply with PCI DSS, EMV, and NPCI guidelines | BE
| UI & Backend for Card Transactions | 3 | Transaction flow, PIN-based authentication | Requires POS/mATM support, secure PIN handling | FE + BE
| ONUS/OFFUS Transaction Handling | 2 | Bank-specific routing logic | Issuer banks' approval required for OFFUS transactions | BE
| Reconciliation & Chargeback Handling | 2 | Settlement policies | Failed transactions must be managed via dispute resolution | BE
| QA and Security Compliance Check | 1 | PCI DSS & EMV certification | Need security audit to ensure compliance | QA
7. Third-Party Cash Deposit | API Integration with Partner Banks | 3 | API availability from banks | Some banks may restrict third-party deposits | BE
| UI & Backend for Cash Deposit Transactions | 3 | UI updates, deposit validation | Need clear communication on deposit limits & fees | FE + BE
| Transaction Reconciliation & Settlement | 2 | Backend validation, dispute handling | Must ensure correct fund allocation and settlement process | BE
| AML & KYC Compliance Handling | 2 | Risk assessment, fraud detection | Must comply with RBI guidelines | BE
| QA and Testing | 1 | Functional & security testing | Ensure transactions do not exceed regulatory limits | QA
8. Remittance/DMT (IMPS & AEPS Fund Transfer) | IMPS API Integration | 3 | NPCI switch API availability | Need confirmation from banking partners | BE
| UI & Backend for Money Transfers | 3 | Transfer workflow, authentication | Requires verification for sender & receiver | FE + BE
| AEPS Fund Transfer Handling | 2 | Aadhaar-based fund transfers | Must comply with Aadhaar-based transaction limits | BE
| Fraud Prevention & Risk Management | 2 | Velocity checks, fraud detection | High-risk transactions need monitoring | BE
| QA and Testing | 1 | Functional & security testing | Test failure scenarios & edge cases | QA
9. BBPS Service – All Billers | BBPS UI Development | 3 | API specs from biller aggregator | Support for multiple biller categories | FE
| BBPS Backend API Integration | 4 | BBPS API access, NPCI guidelines | Transaction reconciliation, response time | BE
| Bill Payment Status & Notifications | 2 | Event-driven updates, retry logic | Some billers may have delayed updates | BE + Notification MS
| Error Handling & Dispute Resolution Flow | 3 | Failure scenarios, refund policies | Dispute process needs clear definition | BE
| Lifecycle for New Billers After First Biller Integration | Timeline varies per biller | BBPS Integration Layer | Requires biller-specific testing & certification | FE + BE + QA
| Requirement Analysis & Onboarding | 2 | API documentation, authentication details | Biller-specific transaction & reconciliation rules | BE
| Development & Integration | 3 | API handlers, status mapping, retries | Custom reconciliation logic per biller | BE
| Testing & Certification | 2 | Functional & stress testing | Compliance with NPCI BBPS guidelines | QA
10. Dual Aadhaar Authentication | UI for Dual Aadhaar Authentication | 2 | Biometric SDK support, UX design | Need clear use cases for SHG/group transactions | FE
| Backend API for Dual Aadhaar Processing | 3 | Aadhaar authentication APIs, NPCI compliance | Must handle two simultaneous Aadhaar authentications | BE
| Transaction Processing & Validation | 2 | Business rules for group authentication | Device compatibility with dual authentication | BE
| Testing and Compliance Checks | 2 | Regulatory security audits | Ensure alignment with Aadhaar-based transaction norms | QA
11. BHIM Aadhaar Pay | Merchant UI Development | 3 | Merchant onboarding requirements | Need merchant KYC and approval process | FE
| Backend API for Aadhaar Pay | 3 | NPCI Aadhaar Pay API | Must ensure secure handling of Aadhaar and bank transactions | BE
| Transaction Processing & Fraud Prevention | 3 | Risk scoring, anomaly detection | Security and fraud prevention critical | BE
| Compliance & Transaction Limits Handling | 2 | NPCI guidelines | Transaction limits and real-time fraud monitoring needed | BE
| Testing & Certification | 2 | UAT & NPCI approval process | Aadhaar Pay certification with NPCI before production rollout | QA
12. FASTag – Issuance and Recharge | UI Development for FASTag Issuance & Recharge | 3 | API availability, KYC flow design | UX for seamless vehicle-tag linking; fraud prevention needed | FE
| Backend API for FASTag Issuance & Recharge | 3 | FASTag provider API integration | Third-party API dependencies; handling recharge failures | BE
| KYC & Vehicle Registration Validation | 2 | RTO/Bank verification process | Need to define document requirements and verification flow | BE
| Admin Panel for FASTag Management | 2 | Agent workflows, approval process | Requires real-time status updates from providers | FE + BE
| QA and Testing | 2 | Functional & security testing | Edge case testing (invalid tags, vehicle mismatches, double charging) | QA
13. Lead Generation for Bank Products | UI for Lead Capture & Submission | 3 | Lead form design, minimal input fields | Fraud detection to prevent fake leads | FE
| Backend API for Lead Processing & Routing | 3 | Bank API access, validation | Compliance with data-sharing regulations; multiple bank integrations | BE
| Omnichannel Notification Setup (WhatsApp, Email, In-App) | 2 | Messaging API integration | Lead nurturing flow; engagement strategy | FE + BE
| Admin Dashboard for Lead Tracking | 2 | Lead management, conversion tracking | Role-based access for bank partners | FE + BE
| QA and Testing | 1 | Functional testing, lead flow validation | Ensuring duplicate prevention & data accuracy | QA
14. Best Finger Detection (BFD) | Device SDK Integration | 2 | UIDAI guidelines, biometric SDK | Device compatibility issues; fallback mechanism for failures | FE + BE
| UI/UX for Fingerprint Capture | 2 | UX research on user guidance | Must ensure proper instructions for users | FE
| Backend Processing for BFD | 2 | Biometric match optimization | Performance tuning for fast response | BE
| QA and Testing | 1 | Edge case handling (fingerprint quality issues) | Need to validate accuracy across diverse user groups | QA
15. Unified Dispute Resolution (UDIR) | UI for Dispute Logging & Tracking | 3 | User input flow, status updates | Categorization of disputes; real-time tracking | FE
| Backend API for Dispute Management | 3 | Bank & AePS dispute handling process | SLA compliance; fraud detection | BE
| Automated Notification System for Status Updates | 2 | Messaging API integration | Ensuring users are updated at every stage | FE + BE
| Admin Dashboard for Dispute Handling | 2 | Role-based access, resolution tracking | Multi-party coordination (banks, NPCI, AePS) | FE + BE
| QA and Testing | 2 | Functional testing, SLA adherence | Validating response times and resolution processes | QA
16. Government Schemes Integration (e.g., PMJJBY, PMSBY, etc.) | UI Development for Scheme Enrollment | 3 | Government guidelines, UX design | Eligibility criteria must be dynamic | FE
| Backend API Integration for Policy Issuance | 4 | Scheme-specific APIs, authentication | API stability & documentation quality | BE
| Premium Payment Processing | 3 | Payment gateway integration | Auto-debit setup with banks required | BE
| Claim Processing Workflow | 4 | Documentation & claim submission rules | Delayed processing timelines for claims | BE
| Notifications & Reminders | 2 | Event-driven updates, retry logic | Policy renewals and reminders must be automated | Notification MS
| Lifecycle for New Government Schemes After First Scheme Integration | Timeline varies per scheme | Government Schemes Management Module | Requires scheme-specific testing & certification | FE + BE + QA
| Requirement Analysis & Onboarding | 2 | Scheme details, API documentation | Eligibility & claim processes may vary | BE
| Development & Integration | 3 | API handlers, status mapping, payments | Premium collection rules may differ | BE
| Testing & Compliance | 2 | Functional & security testing | Must comply with government regulations | QA
17. Final Testing & Deployment | System Integration Testing (SIT) | 2 | Test overall system flow | Dependency on completion of all modules | QA
| User Acceptance Testing (UAT) | 2 | User feedback, final approval | Requires active participation from stakeholders | QA + FE + BE
| Deployment and Go-Live Preparation | 2 | Production environment setup | Must have rollback plans in case of failures | DevOps