## Timeline
Phase | Resources | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | PW | PD
| PM | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 5 | 25
[12 empty] | 0 | 0
BRS | BA | 1 | 1 | [8 empty] | 2 | 10
[12 empty] | 0 | 0
[12 empty] | 0 | 0
Development | [11 empty] | 0 | 0
| UI/UX |  | 1 | 1 | [7 empty] | 2 | 10
| FE |  |  | 2 | 2 | 2 | 2 |  |  |  |  | 8 | 40
| BE |  |  | 2 | 2 | 2 | 2 |  |  |  |  | 8 | 40
| BCE |  |  | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 12 | 60
| QA | [7 empty] | 2 |  |  | 2 | 10
Demo Deployment | [11 empty] | 0 | 0
| BCE | [8 empty] | 1 |  | 1 | 5
| BE | [8 empty] | 1 |  | 1 | 5
| DevOps | [8 empty] | 1 |  | 1 | 5
UAT+Bug Fixing | [11 empty] | 0 | 0
| FE | [9 empty] | 1 | 1 | 5
| BE | [9 empty] | 1 | 1 | 5
| BCE | [9 empty] | 1 | 1 | 5
| QA | [9 empty] | 1 | 1 | 5
[11 empty] | Total | 46 | 230

## Resources
Level | Number | Skill | Acronym
G6 | 1 | Project Manager | PM
G6 | 1 | Business Analyst | BA
G7 | 1 | Blockchain Engineer | BCE
G5 | 1 | Blockchain Engineer | BCE
G5 | 2 | Quality Assurance Engineer | QA
G6 | 1 | Cloud and DevOps | DevOps
G4 | 2 | Frontend Engineer | FE
G5 | 2 | Backend Engineer | BE

## WBS
Milestone | Task | Description
Project Management & Governance | Project initiation | Kick-off workshop with stakeholders and pilot users
Define success criteria and acceptance tests
Identify pilot user groups, roles, and contacts
| Planning & tracking | Create project plan, milestones, sprint schedule
Risk register and mitigation plan
Weekly status reporting and steering checkpoints
| Change & communications | Stakeholder communication plan
User onboarding and training plan for pilot
Requirements & Analysis | Detailed requirements gathering | Confirm data sources (SAP export formats), sample files and fields
Capture reconciliation rules, mapping rules, and business logic
Define discrepancy types and tracking attributes
| Acceptance criteria & test cases | Define user stories and acceptance criteria
Create test plan and success metrics for PoC
Solution Design | High-level architecture | Define WebApp architecture (frontend, backend, storage)
Define integration points for later automated pulls (Backlog)
| Data model design | Entities: SO, PO, GRN, Vendor, ReconciliationRecord, Discrepancy, User, ImportSession
Many-to-many mapping approach and schema design
Data validation and transformation rules
| UI/UX design | Wireframes for core screens: Login/landing, Data Import, Data Explorer/Query
Wireframes for core screens: Reconciliation Dashboard
Wireframes for core screens: Discrepancy Log, Export
Basic interaction flows and error states
Implementation — Backend | Project setup & infra | Dev/test/prod provisioning (or PoC sandbox), CI/CD setup
Database provisioning and migration script strategy
Project Codebase Setup for Backend
| Data import engine | File upload handler, parsing for expected SAP export formats (CSV/Excel)
Validation rules and import session logging
Deduplication and basic normalization
| Reconciliation engine | Implement matching logic for SO–PO–GRN many-to-many relationships
Business rules and formula implementations
Reconciliation status calculation and scoring
| Discrepancy tracking API | Create endpoints for creating, updating, querying discrepancy records
Mapping/Linking discrepancies to source records and import sessions
| Export & reporting API | Simple summary endpoints for dashboards
Endpoints to generate downloadable reconciliation reports (CSV/Excel)
Trigger blockchain event for report exports (store export hash + metadata)
| Blockchain component & integration | Implement blockchain client/component
Implement async queue for blockchain writes with retry/backoff and alerting
Key management integration (secure storage of private keys)
Implement storage of txId/blockHash and write status in audit logs
Admin verification API to compare on-chain hash with off-chain payload
Unit/integration tests for blockchain client
Blockchain Network | Hyperledger Development Netwrok | Provision dev network components (orderer, peers, channels, Certificate Authority) in PoC environment (containerized using Docker Compose)
Deploy minimal chaincode/smart contract to handle event writes and simple queries (store event metadata + payload hash)
Configure identities and MSP for PoC pilot users and application service accounts
Provide network endpoints and credentials to backend blockchain client.
Continuous Chaincode Development
Implementation — Frontend | Project setup & framework | Project Codebase Setup for Frontend
UI framework, routing, authentication integration (PoC minimal)
| Data Import UI | Upload screen, validation feedback, import history
| Data Explorer / Query UI | Search and filter for SO/PO/GRN records, column display, view details
| Reconciliation Dashboard | Reconciliation results list, status badges, match details
Drill-down to linked records and reconciliation rationale
| Discrepancy Log UI | Create/edit discrepancy, view comments/history, status
| Export & Reporting UI | Trigger export and download reports, simple summary cards
Testing & Quality Assurance | Unit & integration tests | Backend logic tests for import and reconciliation
Frontend component tests where applicable
| System & acceptance testing | End-to-end test cases executed with sample SAP exports
Validate reconciliation outcomes against expected results
| User acceptance testing (pilot) | Pilot user walkthroughs, capture feedback and defects
Iteration and bug-fix cycles prior to Go/No-Go

## WBS with Timeline
T = Project Kickoff Day
Milestone | Task | Description | Stakeholder | Reource Types |  | Remarks
Project Management & Governance | Project initiation | Kick-off workshop with stakeholders and pilot users | TSL + Vara | Team | T+1
|  | Define success criteria and acceptance tests | TSL + Vara | PM+BA+TL | T+3
|  | Identify pilot user groups, roles, and contacts | TSL + Vara | PM+BA+TL | T+5
| Planning & tracking | Create project plan, milestones, sprint schedule | Vara | PM+BA+TL | T+5
|  | Risk register and mitigation plan | TSL + Vara | PM+BA+TL | T+5
|  | Weekly status reporting and steering checkpoints | TSL + Vara | PM+BA+TL | TBD
| Change & communications | Stakeholder communication plan | TSL + Vara | PM+BA+TL | T+5
|  | User onboarding and training plan for pilot | TSL + Vara |  | TBD
Requirements & Analysis | Detailed requirements gathering | Confirm data sources (SAP export formats), sample files and fields | TSL + Vara | BA+TL | T+7
|  | Capture reconciliation rules, mapping rules, and business logic | TSL + Vara | BA+TL | T+10
|  | Define discrepancy types and tracking attributes | TSL + Vara | BA+TL | T+10
| Acceptance criteria & test cases | Define user stories and acceptance criteria | Vara | BA+TL | T+15
|  | Create test plan and success metrics for PoC | Vara | BA+TL+QA | T+15
Solution Design | High-level architecture | Define WebApp architecture (frontend, backend, storage) | TSL + Vara | TL | T+5 | It is already done, need to discuss with client Tech Team
|  | Define integration points for later automated pulls (Backlog) | Vara | TL
| Data model design | Entities: SO, PO, GRN, Vendor, ReconciliationRecord, Discrepancy, User, ImportSession | Vara | TL + BE | T+10 | Followed By "Confirm data sources (SAP export formats), sample files and fields"
|  | Many-to-many mapping approach and schema design | Vara | TL + BE | T+10
|  | Data validation and transformation rules | Vara | TL + BE | T+13
| UI/UX design | Wireframes for core screens: Login/landing, Data Import, Data Explorer/Query | Vara | BA + TL + FE + DE | T+10 | Parallely during Requirement Gathering
|  | Wireframes for core screens: Reconciliation Dashboard | Vara | BA + TL + FE + DE | T+15 | Parallely during Requirement Gathering
|  | Wireframes for core screens: Discrepancy Log, Export | Vara | BA + TL + FE + DE | T+20 | Parallely during Requirement Gathering
|  | Basic interaction flows and error states |  |  | On Every Step
Implementation — Backend | Project setup & infra | Dev/test/prod provisioning (or PoC sandbox), CI/CD setup | Vara + TSL | PM + TL | T+7
|  | Database provisioning and migration script strategy | Vara + TSL | PM + TL | T+10
|  | Project Codebase Setup for Backend | Vara + TSL | TL + BE | T + 5
| Data import engine | File upload handler, parsing for expected SAP export formats (CSV/Excel) | Vara | BE | T+15
|  | Validation rules and import session logging | Vara | BE | T+20 | It is next step after "Data model design"
|  | Deduplication and basic normalization | Vara | BE | T+20
| Reconciliation engine | Implement matching logic for SO–PO–GRN many-to-many relationships | Vara | BE | T+25 | Depends Upon "Data model design" and "Capture reconciliation rules, mapping rules, and business logic"
|  | Business rules and formula implementations | Vara | BE | T+25
|  | Reconciliation status calculation and scoring | Vara | BE | T+30 | It will require some more time to minimuze the Mismatches
| Discrepancy tracking API | Create endpoints for creating, updating, querying discrepancy records | Vara | BE | T+25
|  | Mapping/Linking discrepancies to source records and import sessions | Vara | BE | T+25
| Export & reporting API | Simple summary endpoints for dashboards | Vara | BE | T+30
|  | Endpoints to generate downloadable reconciliation reports (CSV/Excel) | Vara | BE | T+25
|  | Trigger blockchain event for report exports (store export hash + metadata) |  |  | T+25
| Blockchain component & integration | Implement blockchain client/component | Vara | BCE | T+10
|  | Implement async queue for blockchain writes with retry/backoff and alerting | Vara | BCE | T+15
|  | Key management integration (secure storage of private keys) | Vara | BCE | T+15
|  | Implement storage of txId/blockHash and write status in audit logs | Vara | BCE | T+20
|  | Admin verification API to compare on-chain hash with off-chain payload | Vara | BCE | T+25
|  | Unit/integration tests for blockchain client | Vara | BCE | N/A | Excluded
Blockchain Network | Hyperledger Development Netwrok | Provision dev network components (orderer, peers, channels, Certificate Authority) in PoC environment (containerized using Docker Compose) | Vara | BCE | T+5
|  | Deploy minimal chaincode/smart contract to handle event writes and simple queries (store event metadata + payload hash) | Vara | BCE | T+10
|  | Configure identities and MSP for PoC pilot users and application service accounts | Vara | BCE | T+10
|  | Provide network endpoints and credentials to backend blockchain client. | Vara | BCE | T+10
|  | Continuous Chaincode Development | Vara | BCE | T+30
Implementation — Frontend | Project setup & framework | Project Codebase Setup for Frontend | Vara | FE | T+5
|  | UI framework, routing, authentication integration (PoC minimal) | Vara | FE | T+7 | Depends upon "Project Codebase Setup for Backend"
| Data Import UI | Upload screen, validation feedback, import history | Vara | FE | T+15 | Depends upon Design
| Data Explorer / Query UI | Search and filter for SO/PO/GRN records, column display, view details | Vara | FE | T+20
| Reconciliation Dashboard | Reconciliation results list, status badges, match details | Vara | FE | T+25
|  | Drill-down to linked records and reconciliation rationale | Vara | FE | T+30
| Discrepancy Log UI | Create/edit discrepancy, view comments/history, status | Vara | FE | T+35
| Export & Reporting UI | Trigger export and download reports, simple summary cards | Vara | FE | T+40
Testing & Quality Assurance | Unit & integration tests | Backend logic tests for import and reconciliation | Vara |  | N/A | Excluded
|  | Frontend component tests where applicable | Vara |  | NA | Excluded
| System & acceptance testing | End-to-end test cases executed with sample SAP exports | TSL + Vara | PM + BA + TL + BE + FE | T+50 | After Completion of "Reconciliation Dashboard"
|  | Validate reconciliation outcomes against expected results | TSL + Vara | PM + BA + TL + BE + FE | T+60 | After Completion of "Export & Reporting UI"
| User acceptance testing (pilot) | Pilot user walkthroughs, capture feedback and defects |  |  | T + 60 + 5 + 5 + 5 | Considered 3 iterations
|  | Iteration and bug-fix cycles prior to Go/No-Go |  |  | T + 65 + 5 + 5 | Considered 3 iterations
|  |  |  | Development Time | T + 75
|  |  |  | Buffer | 11 | 15%
|  |  |  | Estimation | T + 86

## Timeline (Adjusted with WBS)
Phase | Resources | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | PW | PD
| PM | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6 | 30
[14 empty] | 0 | 0
BRS | BA | 1 | 1 | 1 | 0.5 | [8 empty] | 3.5 | 17.5
| TL | 1 | 0.75 | 0.75 | 0.5 | [8 empty] | 3 | 15
[14 empty] | 0 | 0
Development | [13 empty] | 0 | 0
| TL |  | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  |  | 3 | 15
| UI/UX |  | 1 | 1 | 1 | [8 empty] | 3 | 15
| FE | 0.5 | 1 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 13.5 | 67.5
| BE | 0.5 | 1 | 2 | 2 | 2 | 2 | 1 | 1 |  |  |  |  | 11.5 | 57.5
| BCE | 0.5 | 1 | 2 | 2 | 2 | 1 | 1 | 1 |  |  |  |  | 10.5 | 52.5
| QA |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 4 | 20
Demo Deployment | [13 empty] | 0 | 0
| BCE | [7 empty] | 0.25 | 0.75 |  |  |  | 1 | 5
| BE | [7 empty] | 0.25 | 0.75 |  |  |  | 1 | 5
| DevOps | [7 empty] | 0.25 | 0.75 |  |  |  | 1 | 5
[14 empty] | 0 | 0
SAT | FE | [8 empty] | 1 | 1 |  |  | 2 | 10
| BE | [8 empty] | 1 | 1 |  |  | 2 | 10
| BCE | [8 empty] | 0.25 | 0.25 |  |  | 0.5 | 2.5
| QA | [8 empty] | 1 | 1 |  |  | 2 | 10
[14 empty] | 0 | 0
UAT+Bug Fixing | TL | [10 empty] | 0.5 | 0.5 | 1 | 5
| FE | [10 empty] | 0.5 | 0.5 | 1 | 5
| BE | [10 empty] | 0.5 | 0.5 | 1 | 5
| BCE | [10 empty] | 0.5 | 0.5 | 1 | 5
| QA | [10 empty] | 0.5 | 0.5 | 1 | 5
[11 empty] | Total |  |  | 72.5 | 362.5

## WBS (without blockchain) with T
T = Project Kickoff Day
Milestone | Task | Description | Stakeholder | Reource Types |  | Remarks
Project Management & Governance | Project initiation | Kick-off workshop with stakeholders and pilot users | TSL + Vara | Team | T+1
|  | Define success criteria and acceptance tests | TSL + Vara | PM+BA+TL | T+3
|  | Identify pilot user groups, roles, and contacts | TSL + Vara | PM+BA+TL | T+5
| Planning & tracking | Create project plan, milestones, sprint schedule | Vara | PM+BA+TL | T+5
|  | Risk register and mitigation plan | TSL + Vara | PM+BA+TL | T+5
|  | Weekly status reporting and steering checkpoints | TSL + Vara | PM+BA+TL | TBD
| Change & communications | Stakeholder communication plan | TSL + Vara | PM+BA+TL | T+5
|  | User onboarding and training plan for pilot | TSL + Vara |  | TBD
Requirements & Analysis | Detailed requirements gathering | Confirm data sources (SAP export formats), sample files and fields | TSL + Vara | BA+TL | T+7
|  | Capture reconciliation rules, mapping rules, and business logic | TSL + Vara | BA+TL | T+10
|  | Define discrepancy types and tracking attributes | TSL + Vara | BA+TL | T+10
| Acceptance criteria & test cases | Define user stories and acceptance criteria | Vara | BA+TL | T+15
|  | Create test plan and success metrics for PoC | Vara | BA+TL+QA | T+15
Solution Design | High-level architecture | Define WebApp architecture (frontend, backend, storage) | TSL + Vara | TL | T+5 | It is already done, need to discuss with client Tech Team
|  | Define integration points for later automated pulls (Backlog) | Vara | TL
| Data model design | Entities: SO, PO, GRN, Vendor, ReconciliationRecord, Discrepancy, User, ImportSession | Vara | TL + BE | T+10 | Followed By "Confirm data sources (SAP export formats), sample files and fields"
|  | Many-to-many mapping approach and schema design | Vara | TL + BE | T+10
|  | Data validation and transformation rules | Vara | TL + BE | T+13
| UI/UX design | Wireframes for core screens: Login/landing, Data Import, Data Explorer/Query | Vara | BA + TL + FE + DE | T+10 | Parallely during Requirement Gathering
|  | Wireframes for core screens: Reconciliation Dashboard | Vara | BA + TL + FE + DE | T+15 | Parallely during Requirement Gathering
|  | Wireframes for core screens: Discrepancy Log, Export | Vara | BA + TL + FE + DE | T+20 | Parallely during Requirement Gathering
|  | Basic interaction flows and error states |  |  | On Every Step
Implementation — Backend | Project setup & infra | Dev/test/prod provisioning (or PoC sandbox), CI/CD setup | Vara + TSL | PM + TL | T+7
|  | Database provisioning and migration script strategy | Vara + TSL | PM + TL | T+10
|  | Project Codebase Setup for Backend | Vara + TSL | TL + BE | T + 5
| Data import engine | File upload handler, parsing for expected SAP export formats (CSV/Excel) | Vara | BE | T+15
|  | Validation rules and import session logging | Vara | BE | T+20 | It is next step after "Data model design"
|  | Deduplication and basic normalization | Vara | BE | T+20
| Reconciliation engine | Implement matching logic for SO–PO–GRN many-to-many relationships | Vara | BE | T+25 | Depends Upon "Data model design" and "Capture reconciliation rules, mapping rules, and business logic"
|  | Business rules and formula implementations | Vara | BE | T+25
|  | Reconciliation status calculation and scoring | Vara | BE | T+30 | It will require some more time to minimuze the Mismatches
| Export & reporting API | Simple summary endpoints for dashboards | Vara | BE | T+30
|  | Endpoints to generate downloadable reconciliation reports (CSV) | Vara | BE | T+30
Implementation — Frontend | Project setup & framework | Project Codebase Setup for Frontend | Vara | FE | T+5
|  | UI framework, routing, authentication integration (PoC minimal) | Vara | FE | T+7 | Depends upon "Project Codebase Setup for Backend"
| Data Import UI | Upload screen, validation feedback, import history | Vara | FE | T+15 | Depends upon Design
| Data Explorer / Query UI | Search and filter for SO/PO/GRN records, column display, view details | Vara | FE | T+20
| Reconciliation Dashboard | Reconciliation results list, status badges, match details | Vara | FE | T+25
|  | Drill-down to linked records and reconciliation rationale | Vara | FE | T+30
| Reporting UI | Simple summary cards | Vara | FE | T+35
Testing & Quality Assurance | Unit & integration tests | Backend logic tests for import and reconciliation | Vara |  | N/A | Excluded
|  | Frontend component tests where applicable | Vara |  | NA | Excluded
| System & acceptance testing | End-to-end test cases executed with sample SAP exports | TSL + Vara | PM + BA + TL + BE + FE | NA | After Completion of "Reconciliation Dashboard"
|  | Validate reconciliation outcomes against expected results | TSL + Vara | PM + BA + TL + BE + FE | NA | After Completion of "Export & Reporting UI"
| User acceptance testing (pilot) | Pilot user walkthroughs, capture feedback and defects |  |  | T + 35 + 5 + 5 + 5 | Considered 3 iterations
|  | Iteration and bug-fix cycles prior to Go/No-Go |  |  | T + 40 + 5 + 5 | Considered 3 iterations
|  |  |  | Development Time | T + 50
|  |  |  | Buffer | 11 | 15%
|  |  |  | Estimation | T + 86

## Timeline (Adjusted with WBS-wit
Phase | Resources | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | PW | PD
| PM | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 5 | 25
[12 empty] | 0 | 0
BRS | BA | 1 | 1 | 1 | 0.5 | [6 empty] | 3.5 | 17.5
| TL | 1 | 0.75 | 0.75 | 0.5 | [6 empty] | 3 | 15
[12 empty] | 0 | 0
Development | [11 empty] | 0 | 0
| TL |  | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  | 2.5 | 12.5
| UI/UX |  | 1 | 1 | 1 | [6 empty] | 3 | 15
| FE | 0.5 | 1 | 2 | 2 | 2 | 2 | 2 |  |  |  | 11.5 | 57.5
| BE | 0.5 | 1 | 2 | 2 | 2 | 2 | 1 |  |  |  | 10.5 | 52.5
| QA |  |  |  |  | 1 | 1 | 1 |  |  |  | 3 | 15
UAT+Bug Fixing | [11 empty] | 0 | 0
| TL | [7 empty] | 0.5 | 0.5 | 0.5 | 1.5 | 7.5
| FE | [7 empty] | 1 | 1 | 1 | 3 | 15
| BE | [7 empty] | 1 | 1 | 1 | 3 | 15
| QA | [7 empty] | 1 | 1 | 1 | 3 | 15
[11 empty] | Total | 52.5 | 262.5