## Execution Considerations
# | Category | Criteria | Explanation | Marks | Is External Support Required | Vara Remarks
1 | Platform Selection (4 marks) | Name and Version of the Platform (1 mark) | support for smart contracts, privacy features, and consortium management? Is the blockchain platform's name and version clearly mentioned? How well is it justified in terms of compatibility with project needs like | 1 | No
|  | Rationale for Selection (3 marks) | How well is the rationale for choosing the platform explained? Does it cover security, scalability, and performance in relation to the project's objectives? | 3 | No
2 | Distributed Node Architecture (4 marks) | Stakeholder Node Deployment (1 mark) | Does the proposal outline a clear strategy for node deployment across different locations? | 1 | No
|  | Node Access and Permissions (1 mark) | How well is access control for different stakeholders defined? | 1 | Yes | Development team has less visibility on VPN Softwares.
|  | Network Security and Integrity (1 mark) | Does the proposal include sufficient security measures for the node network? | 1 | Yes | Development team has less visibility on firewall softwares
|  | Scalability and Interoperability (1 mark) | How comprehensive are the scalability and interoperability plans for node growth and future integration? | 1 | No and Yes | The development can be done in a scalable fashion, but DevOps is required to scale the compute resource sizes.
3 | Smart Contract Support (3 marks) | Programming Languages, Tools, and Frameworks (1 mark) | Are the programming languages and tools compatible and efficient for the blockchain platform? | 1 | No
|  | Lifecycle Management and Upgradability (1 mark) | Does the proposal include clear strategies for versioning, upgrading, and maintaining smart contracts? | 1 | No
|  | Deployment and Maintenance (1 mark) | How well are smart contract deployment and long-term maintenance strategies explained? | 1 | No
4 | Privacy and Security (2 marks) | Privacy Mechanisms (1 mark) | Are the privacy mechanisms robust and aligned with stakeholder needs? | 1 | No and Yes | If it related to access control to the APIs, we can do it. If it network related, then external support required
|  | Security Protocols (1 mark) | Are the proposed security protocols comprehensive and aligned with the platform's security needs? | 1 | No and Yes | If it related to SSL, HTTPS, TLS, WSS protocol, we can do it. If it network related or node accessisibility related, then external support required
5 | API Management and Security (3 marks) | API Gateway Implementation (1 mark) | Is the approach to API management well-articulated and robust? | 1 | No
|  | Security Measures and Rate Limiting (1 mark) | Are the API security measures, including rate limiting and throttling, clearly defined? | 1 | No
|  | Monitoring and Logging (1 mark) | Does the proposal include an effective plan for real-time monitoring and logging? | 1 | No
6 | Disaster Recovery and Business Continuity (2 marks) | DR and BCP Strategy (1 mark) | Is there a clear and detailed disaster recovery and business continuity plan? | 1 | Yes | Development team is not responsible for Infrastructure management
|  | Automatic Failover Mechanisms and Regular DR Drills (1 mark) | Are there plans for failover mechanisms and regular disaster recovery drills? | 1 | Yes | Development team is not responsible for Infrastructure management
7 | Performance and Scalability Benchmarks (2 marks) | Performance Benchmarks and Load Testing (1 mark) | Are realistic performance benchmarks and load testing plans provided? | 1 | Yes | Both Development and DevOps team required
|  | Monitoring and Optimization (1 mark) | How well does the proposal address ongoing monitoring and optimization for performance issues? | 1 | Yes | Both Development and DevOps team required

## Dev Team Composition
Category | Role |  | Cost Per Day | Total Cost | Monthly Cost | Team | Total Involvement | Cost
Executive Team | Relationship Manager | 1 | 5000 | 5000 | 100000 | Executive Team | 180 | 2880000
| Project Manager | 1 | 6000 | 6000 | 120000 | Software Architect | 200 | 6000000
| Business Analyst | 1 | 5000 | 5000 | 100000 | Development Team T1 | 200 | 4700000
[6 empty] | Development Team T2 | 200 | 4700000
|  |  | Cost/Manday | 16000 | 320000 | Development Team T3 | 85 | 1997500
Software Architect | Solution Architect | 1 | 10000 | 10000 | 200000 |  | Total | 20277500
| DBA | 0 | 8000 | 0 | 0
| DevOps Engineer | 2 | 10000 | 20000 | 400000
|  |  | Cost/Manday | 30000 | 600000
Development Team | Team Lead | 1 | 8000 | 8000 | 160000
| Full Stack Developer | 0 | 7000 | 0 | 0
| BE Developer | 0 | 5000 | 0 | 0
| FE Developer | 0 | 3500 | 0 | 0
| BC Developer | 2 | 6000 | 12000 | 240000
| QA Engineer | 1 | 3500 | 3500 | 70000
|  |  | Cost/Manday | 23500 | 470000

## Breakdown and Open Questions
# | Component Name | Breakdown | Team | Resources | Estimation | End | Remarks
Base Project Setup
1 | Initial Project Setup and Produrement | Procurement of all InOrganic Resources |  | PM1 | 5 | T+5
1.2 |  | Project Management Tool Setup |  | PM1 | 3 | T+8
1.3 |  | Git Repository Setup and granting access |  | TL1 | 3 | T+5 | Assuming T+2 days taken for getting the platform accesss
1.4 |  | Base Project setup with all required server and UI components. Dockerization for Local Development |  | TL1 | 3 | T+8
1.5 |  | Dev Server Setup, VPN and others server components |  | DO1 | 5 | T+10 | Assuming T+5 days taken for getting the platform accesss. Although the development environment belongs to Bidder
1.6 |  | CI/CD Pipelines |  | DO1 | 5 | T+10
1.6 |  | Hyperledger Network Setup |  | BD1 | 5 | T+10
1.7 |  | Investigation on Existing System |  | BA1,TL1 | 30 | T+35 | Assuming Starting from T+5
2 | Organization Module, User Module and Permission Module | User and Organization Module | T1 | BE1, FE1 | 10 | T+20 | Assuming T+10 days taken to setup all the resources - Organization Creation - User Management
2.2 |  | Role based Permission Module (FE, BE) | T1 | BE1, FE1 | 5 | T+25
2.3 |  | Organization On-Boarding Process | T1 | BE1,FE1,DE1 | 10 | T+35
2.4 |  | 8.1.10 Integration with NSWS | T2 | BE1, BD1 | 20 | T+30 | Second team working on this part from T+10
2.4 |  | Chaincode Development | T1 | BD1 | 25 | T+35 | User and organization registration process intimation - accreditation approvals, and compliance checks.
REC Issuance (Starts at T+30)
3 | Entity Registration for RE Certificate | Registration of REC Eligible Entities | T2 | BE1, FE1, DE0.5 | 10 | T+40 | Assuming it can be started after User Organization Module done at T+30
3.2 |  | Registration of REC Obligated Entities | T2 | BE1, FE1, DE0.5 | 10 | T+50 | Starting at T+35
3.3 |  | Chaincode Development for Entity Approval | T2 | BD1 | 20 | T+50 | Chaincodes to capture the approvals of different Stakeholders, Tokenization
4 | REC Issuance Module | REC Balance Credit/Debit and Transactions | T1 | BE1, FE1, DE1, BD1 | 5 | T+40 | Assuming the existing Plarform is successfully done and we have understading of all data points after T+35 Days, point 1.7
4.2 |  | REC Request and Issuance Workflow | T1 | BE1, FE1, DE1 | 15 | T+55 | Public Verification Feature:
4.3 |  | Chaincode Development Regarding REC Issuance and Transactions | T1 | BD1 | 20 | T+55
5 | Payment Module & E-Invoicing Module | Integration of Payment Module | T2 | TL1, FE1, BE1 | 10 | T+60 | Assuming we got the payment gateway approved. This can be started after T+35 (Point 1.7) and Two team can do the job together parallel to 4
5.2 |  | Update Existing module to integrate with With Payment Module | T2 | BE1, BD1 | 15 | T+75 | Update Backend and Chaincode for above modules
5.3 |  | Workflow improvements to include Payment steps where ever required | T1 | FE1, BE1, BD1, DE1 | 20 | T+75 | Implement Purpose Based Payment Automation
5.4 |  | Build the Invoicing Module and GST Integration | T2 | FE1, BE1, BD1, DE1 | 20 | T+95 | After 4.3, first team is free
REC Trading (Starts at T+75)
6 | Registration For Trading | OnBoarding Sellers and Buyers into the platform | T1 | FE1, BE1, BD1, DE1 | 15 | T+90 | Issuing Buyer and Seller Code
6.2 |  | REC Bidding Workflow | T1 | FE1, BE1, BD1, DE1 | 5 | T+95
6.3 |  | REC Price finalization Workflow | T1 | FE1, BE1, BD1, DE1 | 5 | T+100
6.4 |  | REC Settlement Workflow and Bug Fixes for Above | T1 | FE1, BE1, BD1, DE1 | 10 | T+110
7 | Retallying Payments and Refunding |  | T1 |  | 15 | T+125 | Section 10.16
8.1.11 Development of any software required for ease of data transfer and integration between with NOAR portal (Starts at T+95)
8 | Integration with NOAR portal or any other portal |  | T2 |  | 30 | T+125
Reports And Analytics (T+95)
9 | Dedicated team to work on generating different kind of report |  | T3 |  | 65 | T+160
Data Migration from Existing Platform (T+125)
10 | Planning |  | T1 |  | 45 | T+170
Writing the Scripts
Execution
Regorous Testing and Bug Fixing (T+125)
10 | Regorous Testing and Bug Fixing |  | T2 |  | 45 | T+170

## 9.0 Blockchain Platform Technic
Sections | Strategies Need to Provided in the Proposal
9.1. Platform Selection:
Name and Version of the Blockchain Platform:
Rationale for Selection:
9.2. Distributed Node Architecture:
Stakeholder Node Deployment:
Node Access and Permissions:
Network Security and Integrity:
Data Privacy and Compliance:
Scalability and Interoperability:
9.3. Smart Contract Support Requirements
Programming Languages:
Tools and Frameworks:
Lifecycle Management:
Upgradability:
Deployment and Maintenance:
9.4. Privacy and Security Features:
Privacy Mechanisms:
Security Protocols:
9.5. Consortium Management:
Node and Participant Management:
Governance Model:
9.6. Identity Integration Requirements
Identity management Framework:
Verification and Authentication Process:
Interoperability and Compatibility:
9.7. Digital Signature Certificates (DSCs) for Transaction Signing
API Gateway Implementation:
Security Measures:
Rate Limiting and Throttling:
Monitoring and Logging:
Compliance and Reporting:
9.9. Disaster Recovery (DR) and Business Continuity Planning (BCP) Requirements
DR and BCP Strategy:
Data Replication and Backup:
Automatic Failover Mechanisms:
Regular DR Drills:
On-chain Data Protection:
Off-chain Data Protection:
9.10. Performance and Scalability Benchmarks Requirements:
Performance Benchmarks:
Scalability Plans:
Load Testing:
Monitoring and Optimization:
9.11. Service Level Agreement (SLA) Framework
9.12.Licenses Requirements:
Software License Management:

## 10.0 Features
10.10 Smart Contract Automation:
10.11 Identity Management:
10.12 Tokenization of RECs:
10.13 User Access and Wallet Integration:
10.14 Governance:
10.15 Public Verification Feature:
10.16 Payment Gateway Integration:
10.16.1 Transaction Wise Reconciliation and Mapping
10.16.2 Generation of Statement for Unupdated Transactions
10.16.3 Bifurcation of Bank Account Transactions: Incorporate payment gateway data for detailed transaction bifurcation for the following:
10.17 Payment Gateway with GST Filing Integration:
i. Enhance GSTR-1, GSTR-3B filing module to integrate payment gateway data.
ii. Develop procedures to extract and include B2B entity invoice details from payment gateway transactions.
iii. Develop mechanisms to include taxable values.
iv. Based on the database, prepare monthly GSTR-1 & GSTR-3B Returns.
v. Develop reconciliation mechanisms comparing payment gateway data with annual GST data.
10.18 E-invoicing
10.19 Configuration of User Login

## Sheet6
PW = Person Week
Modules |  | ReConnect | Vara |  | N Developers | Dev Time (week) | PW | Risk and Remarks | QA
|  |  |  | 1. Dev Environment setup | 1 | 2 | 2
Users Module | User related permissions | 1 | 1 | 1. Registrer User Id and Permissions | 1 | 2 | 2
Organization Module | 1. Organization Onboarding 2. Eligible Entity Registration | 1 | 1 | 1. Register Organization Id and its type 2. Enroll eligible Entities (back and forth discussion) | 2 | 4 | 8 | - Rewriting may be required as we dont know how much documentation is required for Organziation Registration and Eligible Entities. Accordingly, we need to modify chaincode, probably we need to write new methods. - Dev Time may as per the complexity explored | 1
REC Module | 1. REC Issuance Workflow | 1 | 1 | 1. Approval process of RECs. 2. Issuance of RECs. | 2 | 4 | 8 | 1. REC NFT flow 2. Expirable NFTs | 1
REC Trading | 1. Buyer Seller Onboarding 2. Bidding Workflow 3. Transfer | 1 | 1 | 1. Buyer and Seller registration (Allow/Block flow) 2. Transfer workflow 3. Ownership History | 2 | 4 | 8 |  | 2
Accounting Module | Payments handlers | 1 | 0
Reporting Module | Miscenious reports | 1 | 0
|  |  | Considerations | 1. We need to provide Identity management Framework. Considering the DSC distribution, we may need an internal Hands-On-Experience working with Dongles and submitting txns to Hyperledger
2. Handling Multiple Singatories may increase the difficulties in practical scenarios as the certificates are distributed outside of the eco-system
3. Frequently changing in policies (Channel Level and Smart contract Level), may increase the development time as it requires RBAC(Role Based Access Control) changes in the development process

## Elapsed Time
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19
| PM | [19 empty] | 18 | bar: W1 to W19
0
BRS | [20 empty] | 0
| BA | [19 empty] | 2 | bar: W1 to W2
| BED | [19 empty] | 2 | bar: W1 to W2
0
Development | [20 empty] | 0
| BA | W9: 0.5; W13: 0.5; W15: 1; W16: 1 | 3
| BED |  |  | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  | 26
| QA | [19 empty] | 4 | bar: W9; W13; W15 to W16
0
SIT | [20 empty] | 0
| BA | W17: 0.25 | 0.25
| BED | W17: 0.5 | 0.5
| QA | [19 empty] | 1 | bar: W17
0
UAT+Bug Fixing | [20 empty] | 0
| BA | [19 empty] | 2 | bar: W18 to W19
| BED | [19 empty] | 2 | bar: W18 to W19
| QA | [19 empty] | 2 | bar: W18 to W19
0
0
Go lIve | [20 empty] | 0
| BED | W19: 2 | 2
0
TOTAL |  | 3 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 4.5 | 3 | 3 | 3 | 4.5 | 3 | 5 | 5 | 2.75 | 4 | 6 | 64.75