## Sheet1
| Epic - Feature Scope | Jira | Task Type | Status | Comment
1 | Move to Goerli or Sepolia Ethereum test networks | INV-20092 | EPIC | Committed
1.0 | Investigate Goerli & Sepolia - PoC Comparing ways to obtain test token on both the networks (HUB) | HUB-1548 | Investigate | Done | Closed
1.1 | Investigate Goerli & Sepolia - PoC Comparing ways to obtain test token on both the networks | INV-21064 | Investigate | Done | Closed
1.2 | Deploy smart contract (Inveniam) | INV-21072 | Enabler | DONE/DevOps -Pending | Ready for Release, DevOps Pending
1.3 | Investigate the sections where Ropsten is used (Hub) | HUB-1549 | Investigate | Done | Closed
1.4 | Investigate the sections where Ropsten is used (INV) | INV-21073 | Investigate | Done | Closed
1.5 | Add support for Goerli network (Hub) | HUB-1550 | Enabler | Done | Ready for Release
1.6 | Update Connection Profile with option to select Goerli on Hub | HUB-1551 | Story | PR Review Pending | DevPro Dependencies
1.7 | Update the guideline page for Metamask on Inveniam | INV-21075 | Story | PR Review Pending | DevPro Dependencies
1.8 | Add support for Goerli network (Hub MS) | INV-21195 | Enabler | PR Review Pending | DevPro Dependencies
1.9 | [Investigate] Type 0,1,2 transactions on Goerli Network | INV-22138 | Investigate | Done | Closed
2 | Integrate Hub with Accumulate Blockchain | HUB-997 | EPIC | Committed
2.1 | Create Accumulate Configuration Screen | HUB-1482 | Story | Done | Ready for Release
2.2 | Update Identity Management: Import Wallet, Profile | HUB-1492 | Story | Done | Ready for Release
2.3 | Update Transaction Report Functionality, Email Noifications with Accumulate | HUB-1491 | Story | Under QA | No DevPro Dependencies. BLOCKER - Waiting Response from Accumulate Discord Channel.
3 | Integrate Accumulate as Independent Ledger via Hub | INV-14566 | EPIC | Committed
3.1 | Update Admin Panel with Accumulate Hub Keys | INV-19689 | Story | PR Review | DevPro Dependencies.
3.2 | Add Accumulate to Apps & Integrations | INV-18346 | Story | PR Review | DevPro Dependencies
3.3 | [DLT,Data Room] Accumulate - Connect, Registry, Deploy Functions, Distribute Token, Edit Total Supply, Link to Explorer | INV-19690 | Story | In Progress | PR Required Post Completion. Design Query
3.4 | Extend Multi-chain with Accumulate chain | INV-19692 | Story | Query | Design Dependencies. Queries related to Design
4 | Integrate Inveniam with BNB Smart Chain via Hub | INV-17139 | EPIC | Done | Ready for Release