## Sheet1
Sl No | Task | Module | ETA
1 | Shutdown the application layer | Rest Server MicroserviceMT798 MicroservicePain001 | 6 min | MT798Microservice 0.2.03 -> Pain001Microservice 0.0.8 -> 0.0.8 RestServer 0.2.18 -> 0.3.010 UI 1.1.18 -> 1.2.30-stable
2 | Chaincode Installation | HLF
2.1 | Instantiate lcacc v | Chaincode | 10 min | new 20221111+1
2.2 | Update licc to v | Chaincode | 5 min | 20220805 -> 20221111+1
2.3 | Update a1cc to v | Chaincode | 5 min | 2.1 -> 20221111+1
2.4 | Update a2cc to v | Chaincode | 5 min | 2.1 -> 20221111+1
2.5 | Update dacc to v | Chaincode | 5 min | 2.1 -> 20221111+1
2.6 | Update nncc to v | Chaincode | 5 min | 2.1 -> 20221111+1
3 | Update the rest server | Rest Server
3.1 | Add new Env Variables | .env File | 10 min
3.2 | Build the rest server v | Rest Server | 2 min
3.3 | Update the rest server | Rest Server | 5 min
4 | Update the UI | UI | 2 min
5 | Update MicroserviceMT798 | MicroserviceMT798
5.1 | Add new Env Variables | .env File | 10 min
5.2 | Build the rest server v | MicroserviceMT798 | 2 min
5.3 | Update the rest server | MicroserviceMT798 | 2 min
6 | Restart the application layer | Rest Server MicroserviceMT798 MicroservicePain001 | 15 min
|  | ETA | 89 min
|  | Buffer | 90 min
|  | Total | 179 min | Around 3 hours of maximum downtime will be required

## LC Acceptance
# | Task | Team | Target Date | Actual Date | Status | Remarks
1 | Requirement discussion | TSL/VARA |  |  | Done
2 | Process received MT 748 message from Bank | VARA |  |  | Done | Available in the UAT server
3 | Transaction Action Page for LC Acceptance for Maker/Checker/Approver | VARA |  |  | Done
4 | Dashboard for LC Acceptance | VARA | 2023-10-19 |  | WIP
5 | Transaction Details page for LC Acceptance | VARA | 2023-10-19 |  | WIP
6 | Process swift notification for LC Acceptances | VARA | 2023-10-17 |  | Done | Available in the UAT server
7 | Send 749 samples to bank using swift | TSL/VARA |  | 2023-10-09 | Done
7.1 | Modify as per the feedback from bank |  | 2023-10-17 |  | Done | Not Tested
8 | UAT for flow 1 748 received from bank and 749 sent | TSL/VARA | 2023-10-25
9 | Manual Entry of LC Acceptance |  | 2023-10-25 |  | WIP
10 | Email PDF discussion for LC Acceptance |  | 2023-10-25
11 | Dev+Testing PDF generate process for LC Acceptance |  | 2023-10-31
12 | Enable email channel for LC Acceptance |  | 2023-11-01