## Sheet1
Y Table - Addition |  | Status | QA Deployment Plan
ADDT_AMOUNT | Additional Amount | Ram Sir shared the details with Shruti Mam
TDID_59 -0008 | New Beneficary Name |  | 2022-03-10
SECADV_BANKS | Second Advising Bank - Key
SECADV_BANKL | Second Advising Bank - Name
SECADV_BANKA | Second Advising Bank - Address
SECADV_SWIFT | Second Advising Bank - Swift
SECADV_ZZACCOUNT | Second Advising Bank - Account
Swift Logics
ADDT_AMOUNT | Swift 39C in MT 700 | Done | 2022-03-11
SECADV_BANKS | Not be used
SECADV_BANKL | Not be used
SECADV_BANKA | Not be used
SECADV_SWIFT | Swift 57A in MT 700, This to be called only when this data is avalaible in Jason or else present logic to be there | Done | 2022-03-11
SECADV_ZZACCOUNT | Not be used
TDID_59 -0008 | Swift field 59 in MT 700, This to be called only when this data is avalaible in Jason orelse present logic to be there | Done | 2022-03-11
UI Changes
Dash Board | Add New Mannual Field - HSS Code (Input Only 8 Digit Mandatory) and this to be mapped in MT 770 as below | Done | 2022-03-10
Swift Mapping | MT 770 – 21E - /HSSCODE/502410817 (HSSCODE is Hard Coded) | Done | 2022-03-11
Dash Board | Pending Task LC and Non LC to be merged, Dashboard to remain Same | Done | 2022-03-10
Dash Board | File Sent Attachement Link (MT 770, 700, 701) | Done | 2022-03-10
Dash Board | Mobile Screen restore to old version | Mobile UI enabled. WIP for LC mobile UI. | 2022-03-10