## QBC Project
PROJECT TRACKING TEMPLATE | [6 empty] | Smartsheet Tip ➜ | Customize the list of possible statuses and priorities to the right so that the Status and Priority columns can use standardized values. |  |  |  | STATUS KEY | PRIORITY KEY
[12 empty] | On Hold | Low
PROJECT TITLE |  | [Project's title] |  |  |  |  | COMPANY NAME | [Company's name] |  |  |  | Not Yet Started | Medium
PROJECT MANAGER |  | [Project Manager's name] |  |  |  |  | DATE | 2018-03-12 |  |  |  | In Progress | High
Complete
PROJECT DETAILS | [7 empty] | DELIVERABLES
STATUS | PRIORITY | START DATE | END DATE | DURATION | ASSIGNED TO | TASK NAME | DESCRIPTION | DELIVERABLE | % DONE | ESTIMATED HOURS | ACTUAL HOURS
QBC Scanner | [8 empty] | 0% | 0 | 0
In Progress | High | 2021-09-20 | 2021-09-23 | 4 | Sthitadhi Roy | Basic Requirement | Please refer to the project document |  | 0% | 0 | 0
Not Yet Started | High | 2021-09-24 | 2021-09-25 | 2 | Sthitadhi Roy | Plan of execution | Need to breakdown the task into smaller steps and submit to Blockchain CoE. |  | 0% | 0 | 0

## ICR
PROJECT TRACKING TEMPLATE | [6 empty] | Smartsheet Tip ➜ | Customize the list of possible statuses and priorities to the right so that the Status and Priority columns can use standardized values. |  |  |  | STATUS KEY | PRIORITY KEY
[12 empty] | On Hold | Low
PROJECT TITLE |  | [Project's title] |  |  |  |  | COMPANY NAME | [Company's name] |  |  |  | Not Yet Started | Medium
PROJECT MANAGER |  | [Project Manager's name] |  |  |  |  | DATE | 2021-09-17 |  |  |  | In Progress | High
Complete
PROJECT DETAILS | [7 empty] | DELIVERABLES
STATUS | PRIORITY | START DATE | END DATE | DURATION | ASSIGNED TO | TASK NAME | DESCRIPTION | DELIVERABLE | % DONE | ESTIMATED HOURS | ACTUAL HOURS
Intercompany Reconciliation | [8 empty] | 80% | 0 | 0
In Progress | High | 2021-09-17 | 2021-09-17 | 1 | Jamil | Chaincode Folder Structure |  |  | 100% | 0 | 0
In Progress | High | 2021-09-17 | 2021-09-21 | 5 | Jamil | DataLake [ chaincode ] | Need to breakdown the task into smaller steps and submit to Blockchain CoE. |  | 80% | 0 | 0
In Progress | High | 2021-09-17 | 2021-09-21 | 5 | Soumya | Master tables [ chaincode ] |  |  | 50% | 0 | 0
Complete | Medium | 2021-09-17 | 2021-09-17 | 1 | Soumya | Create REST EndPoints | End points for 1. Organization 2. Company 3. Company account |  | 100%
In Progress | High | 2021-09-17 | 2021-09-21 | 5 | Jamil | Review master [ chaincode ] | Adjust according to the need of data pushing into the system. |  | 50% | 0 | 0
Complete | Low | 2021-09-17 | 2021-09-18 | 2 | Jamil | Scripts to push data |  |  | 100% | 0 | 0
In Progress | High | 2021-09-17 | 2021-09-21 | 5 | Jamil / Soumya | Test the implementation | Master data creation. Data pushing into the system. LineItem bifurcation. |  | 80% | 0 | 0