## Resource Management
Project Wise Allocation
Sl No | Name | Role | Function | Skills | Status | Inveniam | CertCheck | TubeNxt | Trade Finance | eKyc | ICR | Attendance Tracker | Bond Vue
1 | Ankita | PM
2 | Sanchari | BA
3 | Moumita | QA
4 | Saurabh | QA
5 | Jayant | BA
6 | Jamil | Developer + Lead | FS |  |  | 1 |  |  | 1
7 | Yogesh | Developer | FE | Angular (React, NodeJs) | Resigned | 100 %
8 | Sounajit Das | Developer | B | NodeJs, Solidity (GoLang, React) |  | 100 % | [6 empty] | 1
9 | Soumyajit Ghosh | Developer | B | NodeJs, GoLang, Hyperledger |  | 50 % |  | 50 %
10 | Animesh | Developer | FS | NodeJs, Angular, Solidity |  | 100 % | [6 empty] | 1
11 | Shibham | Developer | F | Angular | Resigned - Accepted | 100 -> 0 %
12 | Arvind | UX | UX |  |  | 100 %
13 | Debopriya | QA Intern
14 | Rajkumar | Developer | F | Angluar, React |  | 0 -> 100 % | 100 -> 0 %
15 | Biswajit | Developer | Backend - Lead (BE+Server) | NodeJs |  |  | 100 %
16 | Mobinul | Developer | Backend | NodeJs (React) | [5 empty] | 100 %
17 | Dipro | Developer | FS (F+BC+Server) | Angular, React, NodeJs, Golang, Hyperledger |  |  |  | 70 % |  | 30 %
18 | Bibhav | Developer | FS (F+B+ Server) | React, NodeJS, GoLang | [6 empty] | 100 % | 100 -> 0 %
19 | Abhishek | Developer | B (BC + Server) | NodeJs, GoLang, Hyperledger | [6 empty] | 100 % | 100 -> 0 %

## Project Allocation
Non-Inveniam Projects
|  |  |  | Developers | Abhishek | Baivabh
Sl | Project Name | PM | BA | QA | Developers
| CertCheck | Kirtik |  | Debopriya | 1. Biswajit 2. Mobinul 3. Rajkumar
| ICR - New |  |  |  | 1. Baivabh 2. Abhishek 3. Rajkumar
| e-KYC |  |  |  | 1. Soumyajit Ghosh 2. Dipro 3. Mobinul
| TSL TubeNxt |  | Sanchari |  | 1. Soumyajit Ghosh 2. Dipro
| TSL Tradefinance |  | Sanchari |  | 1. Jamil 2. Abhishek
| TubeNxt Productization |  | Jamil |  | 1. Jamil
| BondVue | Sanchari | Sanchari |  | 1. Jamil (Consultant) 2. Soumyajit 3. Animesh 4. Mobinul (during Internship)
| Inveniam | Kirtik -> Ankita | Jayant (50%) Sanchari (50%) | Saurabh, Moumita | 1. Jamil 2. Soumajit Das 3. Soumyajit Ghosh 4. Animesh Kotka 5. Yogesh Majila 6. Shivam Gaur

## CertCheck
CertCheck
|  |  |  | Developers | Biswajit | Mobinul
Type | Task | Explanation/Breakdown | Assignees | Target Date | Actual Delivery Date | Status

## ICR
Intercompany Reconciliation
|  |  |  | Developers | Abhishek | Baivabh
Type | Task | Explanation/Breakdown | Assignees | Target Date | Actual Delivery Date | Status | Comments
Discussion | Grooming - ICR Process |  | Jamil |  |  | Done
Discussion | Grooming - Transaction Table |  | Jamil |  |  | Done
Discussion | Grooming - Match Set and Pass Rules |  | Jamil |  |  | Done
BE | Transaction Schema Module |  | Jamil |  |  | Done
BE | Tranaction Entry using Schema defined by the user |  | 1. Baibhav 2. Abhishek |  |  | Done
Discussion | Create Pass Rule engine |  | Jamil |  |  | Done
BE | Create Pass Rule structure and basic functionality execution |  | 1. Baibhav 2. Abhishek |  |  | Done
BE | Create Match Set and Pass Rules |  | 1. Baibhav 2. Abhishek 3. Jamil |  |  | Done
Discussion | Watch Blackline Demo videos [TSL Archive] |  | 1. Baibhav 2. Abhishek |  |  | Done
BE | Find Match Set results using Match Sets |  | Baibhav | 2024-05-17
Review | Review, Test and Refactor BE development for transaction matching with Match Set and Pass Rule |  | Jamil | 2024-05-22 | 2024-05-22 | Done
Testing | Prepare DataSet for MatchSet testing |  | 1. Baibhav 2. Abhishek | 2024-05-24 | 2024-05-24 | Done
Testing | Demo to the QA for futher testing |  | 1. Baibhav 2. Abhishek | 2024-05-24 |  |  | Some observation on PassRule execution is observed,need to be resolved.
QA | Testing by QA |  | Debopriya
Discussion | Wireframes for Transaction Schema, transaction table |  | 1. Baibhav 2. Abhishek 3. Jamil | 2024-05-24 |  |  | Jamil is not available due to Inveniam Code Freeze day
Discussion | Wireframes for Pass Rule and Match Set |  | Jamil | 2024-05-24 |  |  | Jamil is not available due to Inveniam Code Freeze day
Demo | Backend Demo with Complete Flow - Transaction to Match Set results |  |  | 2024-05-24 |  |  | Some observation on PassRule execution is observed,need to be resolved.
Design | Fingma Design for Transaction Schema, transaction table |  | Team | 2024-05-28
Design | Fingma Design for Match Set and Pass Rules |  |  | 2024-05-28
BE + CC | User Module |  | 1. Abhishek 2. Jamil | 2024-05-29
CC | Transaction Schema Module |  | 1. Abhishek 2. Jamil | 2024-05-29
CC | Transaction Ledger Entry |  | 1. Abhishek 2. Jamil | 2024-05-29
CC | Transaction Ledger Entry Organization Admin |  | Abhishek | 2024-06-04
UI | Login Screen |  | Rajkumar | 2024-05-30
UI | Ledger Book Create and Transaction Schema |  | Rajkumar | 2024-05-31
UI | Listing Ledger Book and Update Feature |  | Baibhav | 2024-05-31
UI | Create Match Set and Pass Rules |  | 1. Rajkumar 2. Baibhav | 2024-06-04
UI | Update Match Set and Pass Rules |  | 1. Rajkumar 2. Baibhav | 2024-06-06
UI | Run Match Set and View Results |  |  | 2024-06-07
Discussion | Netting, Settling and Balancing of Transactions and Ledger Accounts |  | Jamil | 2024-06-07
Discussion | Report Preparation |  | Jamil | 2024-06-07
Disucssion | Realtime Matching Rule Engine Principles |  | Jamil | 2024-06-11
Discussion | Architecting Report Preparation Module |  | Jamil | 2024-06-12
BE | PoC on Report Preparation |  | Jamil | 2024-06-14

## e-KYC
e-KYC - (need to rethink)
|  |  |  | Developers | Mobinul | Dipro
Type | Task | Explanation/Breakdown | Assignees | Target Date | Actual Delivery Date | Status
Recover | [Recover] Run the KYC platform on cloud
BE | API integration for PAN e-verification | deepvue.tech
FE | UI for PAN e-verification | deepvue.tech
BE | API integration for AADHAR e-verification | deepvue.tech
FE | UI for AADHAR e-verification | deepvue.tech
BE | API integration for Voter ID e-verification | deepvue.tech
FE | UI for Voter ID e-verification | deepvue.tech
Discussion | v-KYC integration using 3rd party vendor
Discussion | Demo Session with v-KYC vendor | HyperVerge |  | 2024-05-08 | 2024-05-08
BE | Integration of v-KYC |  | 1. Jamil 2. Soumyajit | 2024-05-17
FE | UI for v-KYC |  | 1. Jamil 2. Soumyajit | 2024-05-17

## TSL TubeNxt
TSL TubeNxt
[6 empty] | Developers | Dipro | Soumyajit Ghosh
Type | Priority | Task | Explanation/Breakdown | Assignees | Target Date | Actual Delivery Date | Status | Comments
CC | Critical | MIgrate HLF from 1.4.7 to 2.4.9 |  | 1. Dipro 2. Jamil | 2024-06-07
Support Work |  |  |  | 1. Dipro 2. Soumyajit Ghosh

## TSL TradeFinance
Trade Finance
[6 empty] | Developers | Abhishek | Dipro
Type | Priority | Task | Explanation/Breakdown | Assignees | Target Date | Actual Delivery Date | Status | Comments
CC | Critical | MIgrate HLF from 1.4.7 to 2.4.9 |  | 1. Abhishek 2. Dipro | 2024-06-07
Support Work |  |  |  | Jamil

## Productization TubeNxt
Productization
[6 empty] | Developers | Dipro
Type | Priority | Task | Explanation/Breakdown | Assignees | Target Date | Actual Delivery Date | Status | Comments
UI | Critical | Theming and Cosmetic Text Changes |  | Dipro | 2024-05-22 | 2024-05-22 | Done
BE | Normal | Generate QR for the TC |  | Dipro | 2024-05-23 | 2024-05-23 | Done
BE | Normal | Embed QR code into the TC |  | Dipro | 2024-05-24
Discussion |  | Rethink the Features of TubeNxt |  | 1. Jamil 2. Sanchari | 2024-05-31